## OnlineSprint (hidden)
|  |  | Peer Review | Rajesh
|  |  | Alpha Release : Release to QA | Bhavana
Project Name | Technology | Client | Activities | Resource Name | Comments | Planned Start Date | Duration | Planned End Date | Status | Actual Start | Actual End
Avengers | Java | Playtech
|  |  | Pre Development | Bhavana |  |  |  |  | Open
|  |  | Kickoff | Bhavana |  |  |  |  | Open
|  |  | Base Game | Bhavana |  |  |  |  | Open
|  |  | Paytable Screens | Bhavana |  |  |  |  | Open
|  |  | Stack wild/ expanding wild feature | Bhavana |  |  |  |  | Open
|  |  | Random Wild | Bhavana |  |  |  |  | Open
|  |  | Freegames | Bhavana |  |  |  |  | Open
|  |  | Anticipation | Bhavana |  |  |  |  | Open
|  |  | Sounds | Bhavana |  |  |  |  | Open
|  |  | Bonus | Bhavana |  |  |  |  | Open
|  |  | Server Integration | Bhavana |  |  |  |  | Open
|  |  | Peer Review | Rajesh |  |  |  |  | Open
|  |  | Peer Review Fixes | Bhavana |  |  |  |  | Open
|  |  | Alpha Release | Rajesh |  |  |  |  | Open
|  |  | QA & Rework | Bhavana + QA |  |  |  |  | Open
|  |  | Beta Release | Rajesh |  |  |  |  | Open

## MobileSprint
Peer Review | Rajesh + Pavan
Alpha Release : Release to QA | Pavan
Activities | Resource Name | Comments | Planned Start Date | Duration | Planned End Date | Status | Actual Start | Actual End
PREDEVLOPMENT PROCESS | [5 empty] | Open
Game/Demo/Flow/Feature Understanding | Abhinav |  | 2014-05-26 | 0.5 |  | Open
Assets Analysis of standrad 1.6 resolution | Abhinav |  |  | 0.5 |  | Open
Assets Analysis of standrad 1.7 resolution | Abhinav |  |  | 0.5 |  | Open
Assets Analysis of standrad 1.3 resolution | Abhinav |  |  | 0.5 |  | Open
Assets Analysis of low 1.6 resolution | Abhinav |  |  | 0.5 |  | Open
Assets Analysis of low 1.7 resolution | Abhinav |  |  | 0.5 |  | Open
Assets Analysis of low 1.3 resolution | Abhinav |  |  | 0.5 |  | Open
API Understanding Base Game Request Response | Abhinav |  |  | 0.5 |  | Open
API Understanding Free Game Request Response | Abhinav |  |  | 0.5 |  | Open
API Understanding Expanding Wild Response | Abhinav |  |  | 0.5 |  | Open
API Understanding Random Wild Response | Abhinav |  |  | 0.5 |  | Open
Kick Off |  |  |  | 0.5 |  | Open
BASE GAME IMPLEMENTATION | [5 empty] | Open
Assets Replacement for Base Game standard 1.6 resolution | Abhinav |  |  | 1 |  | Open
Jason Integration for Base Game standard 1.6 resolution | Abhinav |  |  | 1 |  | Open
Base Game Broken Handling | Abhinav |  |  | 1 |  | Open
FREE GAME IMPLEMENTATION | [5 empty] | Open
Assets Replacement for Free Game standard 1.6 resolution | Abhinav |  |  | 1 |  | Open
Free Game Re-Trigger Handling | Abhinav |  |  | 1 |  | Open
Free Game Broken Handling | Abhinav |  |  | 1 |  | Open
Anticipation Animation | Abhinav |  |  | 1 |  | Open
PAYTABLE IMPLEMENTATION | [5 empty] | Open
Assets Replacement for Paytable | Abhinav |  |  | 1 |  | Open
Paytable Localisation | Abhinav |  |  | 1 |  | Open
EXPANDING WILD IMPLEMENTATION | [5 empty] | Open
Expanding Wild Functionality Implemntation | Abhinav |  |  | 1 |  | Open
Expanding Wild Animation Implemntation | Abhinav |  |  | 1 |  | Open
Expanding Wild Payouts Verification | Abhinav |  |  | 1 |  | Open
RANDOM WILD IMPLEMENTATION | [5 empty] | Open
Random Wild Functionality Implemntation | Abhinav |  |  | 1 |  | Open
Random Wild Animation Implemntation | Abhinav |  |  | 1 |  | Open
Random Wild Payouts Verification | Abhinav |  |  | 1 |  | Open
Sounds Implementation for Base Game | Abhinav |  |  | 0.5 |  | Open
Sounds Implementation for Free Game | Abhinav |  |  | 0.5 |  | Open
Sounds Verfication on all devices | Abhinav |  |  | 1 |  | Open
Server Integration & Verfication for Base Game | Abhinav |  |  | 1 |  | Open
Server Integration & Verfication for Free Game | Abhinav |  |  | 1 |  | Open
Server Integration & Verfication for Expanding Wild | Abhinav |  |  | 1 |  | Open
Server Integration & Verfication for Random Wild | Abhinav |  |  | 1 |  | Open
Server Integration & Verfication for Jackpot | Abhinav |  |  | 1 |  | Open
Porting on standard_1.7 Resolution | Meenakshi |  |  | 1 |  | Open
Complete Verification on associated device | Abhinav |  |  | 1 |  | Open
Porting on standard_1.3 Resolution | Meenakshi |  |  | 1 |  | Open
Complete Verification on associated device | Abhinav |  |  | 1 |  | Open
Porting on low_1.6 Resolution | Meenakshi |  |  | 1 |  | Open
Complete Verification on associated device | Abhinav |  |  | 1 |  | Open
Porting on low_1.3 Resolution | Meenakshi |  |  | 1 |  | Open
Complete Verification on associated device | Abhinav |  |  | 1 |  | Open
Porting on low_1.7 Resolution | Meenakshi |  |  | 1 |  | Open
Complete Verification on associated device | Abhinav |  |  | 1 |  | Open
Functionality Peer Review | Rajesh + Pavan |  |  | 1 |  | Open
Animation and Sounds Peer Review | Rajesh + Pavan |  |  | 1 |  | Open
Payouts Peer Review | Rajesh + Pavan |  |  | 1 |  | Open
Functionality Peer Review Fixes | Shashank |  |  | 1 |  | Open
Animation and Sounds Peer Review Fixes | Shashank |  |  | 1 |  | Open
Payouts Peer Review Fixes | Shashank |  |  | 1 |  | Open
Alpha Release | Pavan |  |  | 1 |  | Open
QA & Rework | Abhinavk + QA |  |  |  |  | Open
Beta Release | Rajesh |  |  |  |  | Open

## ServerSprint
Peer Review | Rajesh
Alpha Release : Release to QA | Gopal
Activities | Resource Name | Comments | Planned Start Date | Duration | Planned End Date | Status | Actual Start | Actual End
Set up Game Configuration. | Gopal |  |  |  |  | Open
Base Game Implementation | Gopal |  |  |  |  | Open
Free Game Implementation. | Gopal |  |  |  |  | Open
Expanding Wild Implementation | [5 empty] | Open
Complete Thought Process | Gopal |  |  |  |  | Open
Complete Development Approach Discussion | Gopal |  |  |  |  | Open
Impementation | Gopal |  |  |  |  | Open
Random Wild Implementation | [5 empty] | Open
Complete Thought Process | Gopal |  |  |  |  | Open
Complete Development Approach Discussion | Gopal |  |  |  |  | Open
Random Wild Impementation | Gopal |  |  |  |  | Open
Replay Implementation & Verification | Gopal |  |  |  |  | Open
Profile Creation & Verification | Gopal |  |  |  |  | Open
Complete Integration Testing | Gopal |  |  |  |  | Open
Unit Testing | Gopal |  |  |  |  | Open
RTP Testing (PRED Testing) | Gopal |  |  |  |  | Open
Permutation & Distribution Testing | Gopal |  |  |  |  | Open
Exploit Testing | Gopal |  |  |  |  | Open
Alpha Release | Rajesh |  |  |  |  | Open
Open
Beta Release | Rajesh |  |  |  |  | Open